## Sheet1
# | Task | Assignee | Start Date | End Date | Status | Notes
1 | Complete draft of digital literacy curriculum | IAA | 2023-09-18 | 2023-10-14 | In Progress
2 | Conduct preliminary assessment of foundational skills curriculum | REDF/BCOE | 2023-09-28 | 2023-10-14 | In Progress
3 | Review draft of digital literacy curriculum | REDF/BCOE | 2023-10-16 | 2023-10-20
4 | Complete draft of foundational skills curriculum | IAA | 2023-10-16 | 2023-10-27 |  | Assumes minimal edits, primarily reformating
5 | Review foundational skills curriculum (including SEL principles) | REDF/BCOE | 2023-10-16 | 2023-11-03 |  | Can begin review immediately using Accenture materials
6 | Incorporate additional SEL materials | BCOE | 2023-11-06 | 2023-11-10
7 | Finalize foundational and digital literacy curriculum | IAA | 2023-11-13 | 2023-11-24 |  | Timeline dependent on level updates necessary
8 | Complete linkage agreements with preliminary RAP partners | BCOE | 2023-10-09 | 2023-11-17
9 | Develop draft of technical skill curiculum for RAP partner #1 | IAA | 2023-11-20 | 2024-12-01 |  | Start date dependent on completing linkage agreeements, timeline depending on level of effort and length of technical skill module
10 | Review draft of technical skill curiculum for RAP partner #1 | REDF/BCOE | 2023-12-04 | 2024-12-08
11 | Finalize technical skill curiculum for RAP partner #1 | IAA | 2023-12-04 | 2024-12-22